## Trang tính1
e P r o j e c t s S t a t u s R e p o r t
| Name | Thái Phát
| Enrollment No. | Student1693582
| Name | La Vĩ Quyền
| Enrollment No. | Student1693584
Name
Enrollment No.
| Curriculum | ACCP AI 7236
| Semester | 2
| Centre Name | FPT Aptech Viet Nam
Eprojects Details | Eproject Title | EduCenter Management System
| Duration of the projects | 8 Weeks
| Start Date (DD/MMM/YYYY) | 09-Oct-2026
| End Date (DD/MMM/YYYY) | 05-Dec-2026
Projects Status / Mentoring | 1st Status | We have done the 1st Review (Problem Definition, Customer Requirements Specifications, Project Plan) and the 2nd Review (DFD, ERD, Table Design, Relationship Diagram, Site Map, Algorithm) of the documentation. A working prototype of the 5 modules runs with Docker Compose and passes 15/15 automated API tests.
| Sent Date (DD/MMM/YYYY) | 23-Oct-2026
| Snapshot | Yes
| Description / Review Document | 1st Review and 2nd Review in one pdf file
| Remarks | Next: complete the remaining screens (change password, parent-child link, edit score), add CI and the AI Coach limit test, then Review 3 (screens, testing) by 13-Nov-2026.
2nd and Final Status
Sent Date (DD/MMM/YYYY)
Snapshot
Description / Review Document
Remarks
Students comment | How our (eprojects team) suggestion helped you
Feedback / Remarks